Streetscape Committee Meeting

Thursday, Feb 15, 2024 - 9:00 am Town Building

Agenda & Update from January & Early February

1)     Phase V Design and Construction Status Update:

- Thrasher has been paid for their $15,000 30% Design Completion Invoice and the WV-DOH has reimbursed the Town for this Payment. The Town also received the next invoice ($25,000) for completion of the 90% design milestone. I verified that all comments/corrections to the 90% design have been completed by Thrasher – prior to payment. Believe it’s OK to process this payment soon. Sufficient funds are in Streetscape Acct.

- Current completion of the PS&E package is by Feb 16th to support a DOH Letting Date in early Spring.

- Design and Floodplain reviews have been requested by WV-DOH by the Town’s HLC and the County Floodplain organization.

- Current evaluation shows no need for property easements. Alley area for lighting conduit appears to be Town property.

- Current Streetscape Account (End of Jan – includes the $15K for Thrasher) $42,643

2) Street Light Installation Strategy

- Near-Term: Based on Phase V Design Task & Design Funding

  - Thrasher will complete (2) sets of drawings

  - (1) is a 90% plus PSE for the final installation of Phase V lights (DOH “Scope” and Town Task Order include Design for fully installed lights

  - (2) is a 30% Design for seven lights on Mercer Street (would be an extension of the conduit/wiring from Phase V on Independence St.

- Phase VI Tentative Approach for Congress Street (Starting with Design Task if TA Grant is Awarded

  - Focus on a full package for Congress St including all lights

  - Defer Union St portions to later Phase

- Long-Term Strategy

  - Continue to seek installation Grants (Grants Committee & WV Organizations)

  - Provided Preliminary Pricing Info to Grants Committee

3)     2024 Work Plan – What Needs to be Done?

- Provided a Preliminary Pricing Model for incremental contract work to install Streetscape-type concrete sidewalks in other parts of Core and Town. Model needs review and test.

- 2024 Timeframe financials – potential cash flows with County and Town H/M funds

  - Cash Match for expected Phase VI Design Funding Agreement ($14,000)

- Longer term planning for Cash Match for Phase VI Construction: ($95,000) – sometime in FY25

- Maintenance Aspects – Lighting Repairs and Maintenance Guides

- Beyond the Six-Block Core – Strategy and Grant Applications